## Activity Library
Sl.NO. | Module | Sub Module | Service Name | Method | Reuse | Resource Pattern | Resource Pattern Name | Request Count | Response Count | URI | Remarks | Service Owner | Dev-Status | Integrated by | Target Date of Integration | Integration status | Functionaltity | Performance | Start Date | End date | % Completion | Comments
1 | Timesheet | Activity Library | Get All Phases | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/activitylibrary/phases |  | Shreenidhi | [6 empty] | 2023-11-28 | 2023-11-29 | 100%
2 | Timesheet | Activity Library | Get All Phases with activities | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/activitylibrary/phases/activities |  | Shreenidhi | [6 empty] | 2023-11-30 | 2023-12-01 | 100%
3 | Timesheet | Activity Library | Add Phase | POST |  | Create | Creating Single Resource |  |  | /iapi/activitylibrary/phase |  | Mahalakshmee | [6 empty] | 2023-11-28 | 2023-11-30 | 100%
4 | Timesheet | Activity Library | Delete Phase | DELETE |  | Delete | Delete Resource |  |  | /iapi/activitylibrary/phase |  | Mounika | [6 empty] | 2023-11-29 | 2023-11-30 | 80%
5 | Timesheet | Activity Library | Edit Phase | PATCH |  | Modify | Modify Multi-Valued Attribute |  |  | /iapi/activitylibrary/phase/{phaseId} |  | Mahalakshmee | [6 empty] | 2023-11-30 | 2023-12-01 | 100%
6 | Timesheet | Activity Library | Add New Activity | POST |  | Create | Creating Single Resource |  |  | /iapi/activitylibrary/activity |  | Mounika | [6 empty] | 2023-11-28 | 2023-12-01 | 80%
7 | Timesheet | Activity Library | Edit Activity | PATCH |  | Modify | Modify Multi-Valued Attribute |  |  | /iapi/activitylibrary/activity |  | Mounika | [6 empty] | 2023-11-30 | 2023-12-01 | 80%
8 | Timesheet | Activity Library | Delete Activity | DELETE |  | Delete | Delete Resource |  |  | /iapi/activitylibrary/activity |  | Saptarshi | [6 empty] | 2023-11-30 | 2023-12-01 | 100%
9 | Timesheet | Activity Library | Get Roles with mapping count | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/activitylibrary/roles/mapcount |  | Saptarshi | [6 empty] | 2023-12-04 | 2023-12-05 | 100%
10 | Timesheet | Activity Library | Get phases and activities mapeed to role | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/activitylibrary/rolesphasemapping |  | Pranjali | [6 empty] | 2023-11-29 | 2023-12-01 | 90%
11 | Timesheet | Activity Library | Get delete reasons | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/activitylibrary/deletereasons |  | Pranjali | [6 empty] | 2023-12-01 | 2023-12-05 | 90%
12 | Timesheet | Activity Library | Map Role to Phase and activity | POST |  | Create | Creating Single Resource |  |  | /iapi/activitylibrary/rolemapping |  | Shreenidhi | [6 empty] | 2023-12-06 | 2023-12-08 | 100%

## Activity Library API Details
S.NO | Module | Service Name | Method | URI | HTTP Status Code(Success) | Application Status Code | Request | Input(Query Parameters) | Response | Status | Remarks
1 | Timesheet | Get all Phases | GET | /iapi/activitylibrary/phases | 200 | 200 | Headers: userId:3276 | For Getting one Phase Details:- phaseId=1 For Search:- search="analysis" isActive="active","inactive","all" | { "statusCode": 200, "status": "SUCCESS", "message": "Phase details Retirieved Succesfully", "result": [ { "phaseId": 1, "phaseName": "Analysis and Design", "isActive": 1, "parentPhaseId": 0, "description":"Main phase description", "subPhaseList": [ { "phaseId": 2, "phaseName": "Analysis and Design", "isActive": 1, "parentPhaseId": 1, "description":"Sub phase description", "subPhaseList":[] } ] } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
2 | Timesheet | Get all Phases with activities | GET | /iapi/activitylibrary/phases/activities | 200 | 200 | Headers: userId:3276 | For Getting one Phase Details:- phaseId=1 For Search:- search="analysis" isActive="active","inactive","all" | { "statusCode": 200, "status": "SUCCESS", "message": "Phase details with activities Retirieved Succesfully", "result": [ { "phaseId": 1, "phaseName": "Analysis and Design", "isActive": 1, "parentPhaseId": 0, "description":"Main phase description", "activityList":[], "subPhaseList": [ { "phaseId": 2, "phaseName": "Analysis and Design", "isActive": 1, "parentPhaseId": 1, "description":"Sub phase description", "subPhaseList":[], "activityList":[ { "activityId":1, "activityName":"UI Design", "description":"UI design and development" } ] } ] } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
3 | Timesheet | Add Phase | POST | /iapi/activitylibrary/phase | 200 | 200 | { "phaseName": "Analysis and Design", "description": "analysis and design phase", "parentPhaseId": null } Headers: userId:3276 |  | { "statusCode": 200, "status": "SUCCESS", "message": "Phase details added successfully", "result": null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
4 | Timesheet | Delete Phase | DELETE | /iapi/activitylibrary/phase | 200 | 200 | { "deleteReasonId":2, "deleteDesciprtion":"This phase is not needed for now" } Headers: userId:3276 | phaseId=1 | { "statusCode": 200, "status": "SUCCESS", "message": "Phase details deleted successfully", "result": null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
5 | Timesheet | Edit Phase | PATCH | /iapi/activitylibrary/phase | 200 | 200 | { "phaseName": "Analysis and Design", "description": "analysis and design phase", "parentPhaseId": null } Headers: userId:3276 | phaseId=2 | { "statusCode": 200, "status": "SUCCESS", "message": "Phase details updated successfully", "result": null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
6 | Timesheet | Add New Activity | POST | /iapi/activitylibrary/activity | 200 | 200 | { "phaseId":1, "activityName": "Analysis and Design", "description": "analysis and design phase" } Headers: userId:3276 |  | { "statusCode": 200, "status": "SUCCESS", "message": "Activity details created successfully", "result": null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
7 | Timesheet | Edit Activity | PATCH | /iapi/activitylibrary/activity | 200 | 200 | { "activityName": "Analysis and Design", "description": "analysis and design phase", "phaseId": 1 } Headers: userId:3276 | activityId=1 | { "statusCode": 200, "status": "SUCCESS", "message": "Activity details updated successfully", "result": null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
8 | Timesheet | Delete Activity | DELETE | /iapi/activitylibrary/activity | 200 | 200 | { "deleteReasonId":1, "deleteDesciprtion":"This phase is not needed for now" } Headers: userId:3276 | activityId=2 | { "statusCode": 200, "status": "SUCCESS", "message": "Activity details deleted successfully", "result": null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
9 | Timesheet | Get Roles with mapping count | GET | /iapi/activitylibrary/roles/mapcount | 200 | 200 | Headers: userId:3276 | search="Developer" roleId=1 | { "statusCode": 200, "status": "SUCCESS", "message": "Role details fetched successfully", "result": [ { "roleId":1, "roleName":"Domain Manager", "phasesCount":10, "activityCount":5, "linkedPhasesList":[1,2,3,4,5,6,7,8,9,10], "linkedActivityList":[1,2,3,4,5] }, { "roleId":2, "roleName":"Service Delivery Manager", "phasesCount":10, "activityCount":5, "linkedPhasesList":[1,2,3,4,5,6,7,8,9,10], "linkedActivityList":[1,2,3,4,5] } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
10 | Timesheet | Get phases and activities maped to role | GET | /iapi/activitylibrary/rolesphasemapping | 200 | 200 | Headers: userId:3276 |  | { "statusCode": 200, "status": "SUCCESS", "message": "Phase details with activities mapped to role Retirieved Succesfully", "result": [ { "phaseId": 1, "phaseName": "Analysis and Design", "isActive": 1, "parentPhaseId": 0, "description":"Main phase description", "activityList":[], "subPhaseList": [ { "phaseId": 2, "phaseName": "Analysis and Design", "isActive": 1, "parentPhaseId": 1, "description":"Sub phase description", "subPhaseList":[], "activityList":[ { "activityId":1, "activityName":"UI Design", "description":"UI design and development" } ] } ] } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
11 | Timesheet | Get delete reasons | GET | /iapi/activitylibrary/deletereasons | 200 | 200 | Headers: userId:3276 |  | { "statusCode": 200, "status": "SUCCESS", "message": "Delete reason fetched Successfully", "result": [ { "reasonId":1, "resonName":"Not required" }, { "reasonId":2, "resonName":"This activity is inactive from now" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
12 | Timesheet | Map Role to Phase and activity | POST | /iapi/activitylibrary/rolemapping | 200 | 200 | Headers: userId:3276 { "activitiesMapped": [ { "activityId": [ 1 ], "phaseId": 1 }, { "activityId": [ 2, 3 ], "phaseId": 2 } ], "fkRoleId": 1 } |  | { "statusCode": 200, "status": "SUCCESS", "message": "Activity mapped to role successfully", "result": null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }

## MIS&Nucleus
Sl.NO. | Module | Sub Module | Service Name | Method | Reuse | Resource Pattern | Resource Pattern Name | Request Count | Response Count | URI | Remarks | Service Owner | Completion Date | % Completion | Dev-Status | Integrated by | Target Date of Integration | Integration status | Functionaltity | Performance
1 | Nucleus | Leave management | Get leave details of employee | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/lms/leavedetails/{empId}
2 | MIS | Resource Allocation | Get Allocation details of employee | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/resourceallocation/allocationdetails |  | Mahalakshmee | 2023-12-25 | 80%
3 | MIS | Timesheet | Get Employee Timesheet Policies | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/timesheet/policy/{empId} |  | Mounika | 2023-12-22 | 80%
4 | MIS | Timesheet | Get ProjectX subcomponents | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/timesheet/projectx/subcomponent/{empId} |  | Mounika | 2023-12-15 | 100%
5 | MIS | Project Details | Get Project Details | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/projectdetails |  | Shreenidhi | 2023-12-19 | 100%
6 | Nucleus | Leave Management | Check if the day is weekend or holiday | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/lms/holidayweekend |  | Saptarshi | 2023-12-15 | 100%

## MIS&Nucleus API details
S.NO | Module | Service Name | Method | URI | HTTP Status Code(Success) | Application Status Code | Request | Input(Query Parameters) | Response | Status | Remarks
1 | Nucleus | Get leave details of employee | GET | /iapi/lms/leavedetails/{empId} | 200 | 200 | Headers: userId:3276 | startDate:2023-11-14 (mandatory) endDate:2023-11-15(optional) | { "statusCode": 200, "status": "SUCCESS", "message": "Leave Details fetched Successfully", "result": [ { "date":"2023-11-14", "isHoliday":"yes", "isWeekend":"no", "isFullDayLeave":"no", "isHalfDayLeave":"no", "isLeaveOnSecondHalf":"no" }, { "date":"2023-11-14", "isHoliday":"no", "isWeekend":"no", "isFullDayLeave":"yes", "isHalfDayLeave":"no", "isLeaveOnSecondHalf":"yes" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
2 | MIS | Get Allocation details of employee with efforts | GET | /iapi/resourceallocation/allocationdetails | 200 | 200 | Headers: userId:3276 | empId:3276 (mandatory) startDate:2023-11-14 (mandatory) endDate:2023-11-15(optional) compId:1 (optional) projectId:1(optional) workorderId:1(optional) | Result when only dates are passed with empId:- { "statusCode": 200, "status": "SUCCESS", "message": "Project Details fetched Successfully", "result": [ { "projectId": 1, "projectName":"ProjectX" }, { "projectId": 2, "projectName":"IAMT-2023" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null } Result when dates,empId and projectId:- { "statusCode": 200, "status": "SUCCESS", "message": "Workorder Details fetched Successfully", "result": [ { "workorderId": 1, "workorderName":"IAMT0220231000" }, { "workorderId": 2, "workorderName":"IAMT0220231001" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null } Result when dates,empId,projectId and workorderId:- { "statusCode": 200, "status": "SUCCESS", "message": "Component Details fetched Successfully", "result": [ { "componentId": 1, "componentNo":"IAMT0220231000-1", "componentName":"MIS" }, { "componentId": 2, "componentNo":"IAMT0220231000-2", "componentName":"Nucleus" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null } Result when dates,empId,projectId,workorderId,compId:- { "statusCode": 200, "status": "SUCCESS", "message": "Milestone and Role Details fetched Successfully", "result": [ { "rolesDetails": [ { "roleId": 1, "roleName": "Developer", "allocStartDate": "2023-11-01", "allocEndDate": "2023-11-30", "noOfDays": 10, "empEffort": 3, "roleEffort": 7 }, { "roleId": 2, "roleName": "Testing", "allocStartDate": "2023-11-01", "allocEndDate": "2023-11-30", "noOfDays": 10, "empEffort": 3, "roleEffort": 7 } ], "milesotoneDetails": [ { "milestoneId": 1, "milestoneName": "MIS" }, { "milestoneId": 1, "milestoneName": "MIS" } ] } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
3 | Timesheet | Get Employee Timesheet Policies | GET | /iapi/timesheet/policy/{empId} | 200 | 200 | Headers: userId:3276 |  | { "statusCode": 200, "status": "SUCCESS", "message": "Timesheet policy for employee retrived successfully", "result": [ { "dateOfJoining": "2023-01-01", "lastWorkingDay": null, "locationDateTime": "2023-11-17", "lastTimesheetFilledDate":"2023-12-03" "timesheetPermissionDetails": [ { "permissionType": 1, "noOfDays": 2 }, { "permissionType": 2, "noOfDays": 2 } ] } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
4 | Timesheet | Get ProjectX subcomponents | GET | /iapi/timesheet/projectx/subcomponent/{empId} | 200 | 200 | Headers: userId:3276 |  | { "statusCode": 200, "status": "SUCCESS", "message": "ProjectX sub component details for employee retrived successfully", "result": [ { "subCompId":1, "subCompName":"ProjectX" }, { "subCompId":2, "subCompName":"Pre-sales and Business Development" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
5 | MIS | Project Details | GET | /iapi/projectdetails | 200 | 200 | Headers: userId:3276 | rmId:3276 projectId:1 workOrderId:1 | When rmId is passed { "statusCode": 200, "status": "SUCCESS", "message": "Project details fetched Successfully", "result": [ { "projectId":1, "projectName":"IAMT" }, { "projectId":2, "projectName":"Airtel" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null } When projectId is passed { "statusCode": 200, "status": "SUCCESS", "message": "Workorder details fetched Successfully", "result": [ { "workOrderId":1, "workOrderName":"IAT0220232000", "description":"IAT workorder 1" }, { "workOrderId":2, "workOrderName":"IAT0220232002", "description":"IAT workorder 2" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null } When WorkorderId is passed { "statusCode": 200, "status": "SUCCESS", "message": "Component details fetched Successfully", "result": [ { "componentId":1, "componentName":"Timesheet development", "componentNo":"IAT0220232000-1" }, { "componentId":2, "componentName":"Skill management development", "componentNo":"IAT0220232000-2" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
6 | Nucleus | Leave Management | GET | /iapi/lms/holidayweekend | 200 | 200 | Headers: userId:3276 | empId:3276 date:2023-12-06 | { "statusCode": 200, "status": "SUCCESS", "message": "Holidat/Weekend details fetched Successfully", "result": [ { "isHoliday": "no", "isWeekend": "yes" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }

## TImesheet
Sl.NO. | Module | Sub Module | Service Name | Method | Reuse | Resource Pattern | Resource Pattern Name | Request Count | Response Count | URI | Remarks | Service Owner | Completion Date | % Completion | Dev-Status | Integrated by | Target Date of Integration | Integration status | Functionaltity | Performance
1 | Timesheet | Employee Flow | View Timesheet details | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/timesheet/view/{empId} |  | Pranjali | 2023-12-25 | 80%
2 | Timesheet | Employee Flow | Save Timesheet Entry | POST |  | Create | Creating Single Resource |  |  | /iapi/timesheet/details
3 | Timesheet | Employee Flow | Edit Timesheet Entry | PATCH |  | Modify | Modify Multi-Valued Attribute |  |  | /iapi/timesheet/details/{timesheetId}
4 | Timesheet | Employee Flow | Delete Timesheet Entry | DELETE |  | Delete | Delete Resource |  |  | /iapi/timesheet/details/{timesheetId} |  | Saptarshi | 2023-12-19 | 100%
5 | Timesheet | Employee Flow | Get Previous Timesheet Entry | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/timesheet/view/previousentry/{empId} |  | Saptarshi | 2023-12-25 | 80%
6 | Timesheet | Master | Get All Timesheet Status | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/timesheet/status |  | Pranjali | 2023-12-15 | 100%
7 | Timesheet | Reporting Manager Flow | View Timesheets | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/timesheet/view/rm
8 | Timesheet | Reporting Manager Flow | Download Timesheets | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/timesheet/view/rm/download
9 | Timesheet | Reporting Manager Flow | Get Reports | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/timesheet/reports |  | Pranjali | 2023-12-15 | 100%
10 | Timesheet | Reporting Manager Flow | Get Report Details | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/timesheet/report/details
11 | Timesheet | Reporting Manager Flow | Download Report Details | GET |  | Query | Query Single Resource All Attributes |  |  | /iapi/timesheet/report/details/download
12 | Timesheet | Reporting Manager Flow | Approve/Reject/Reopen Timesheet | PATCH |  | Modify | Modify Multi-Valued Attribute |  |  | /iapi/timesheet/approvereject

## Timesheet API details
S.NO | Module | Service Name | Method | URI | HTTP Status Code(Success) | Application Status Code | Request | Input(Query Parameters) | Response | Status | Remarks
1 | Employee | View Timesheet details | GET | /iapi/timesheet/view/{empId} | 200 | 200 | Headers: userId:3276 | Filters for View:- viewType:Week,WorkWeek,Month,Day Pagenation:- pageNo:0 offSet:10 To view individual timesheet entry:- timesheetId:1 search:"text" (only applicable when viewType is monthly) | { "statusCode": 200, "status": "SUCCESS", "message": "Timesheet policy for employee retrived successfully", "result": [ { "timesheetId":1, "isSupportTimesheet":0, "isLeaveEntry":0, "date":"2023-01-01", "projectId":2, "projectName":"IAMT", "workOrderId":1, "workOrderNumber":"IAT1120232024", "componentId":1, "componentName":"Timesheet Development", "componentNumber":"IAT1120232024-1", "startTime":"11:00", "endTime":"12:00", "duration":"1 hr", "description":"TImesheet API work", "entryType":1, "activityId":1, "activityName":"Service Development", "phaseId":1, "phaseName":"Service Phase", "projecXSubCompId":null, "milestoneId":1, "milestoneName":"Timesheet API milestone" "callOutEntries":[ { "date":"2023-01-01", "startTime":"11:00", "endTime":"12:00", "duration":"1 hr", "description":"TImesheet API work call out" } ] } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
2 | Employee | Save Timesheet Entry | POST | /iapi/timesheet/details | 200 | 200 | Headers: userId:3276 { "projectId": 1, "workOrderId": 1, "componentId": 1, "milestoneId": null, "projectXSubComponentId": 1, "startDate": "2023-11-20", "endDate": "2023-11-20", "startTime": "11:00", "endTime": "12:00", "entryType": 1, "description": "Worked on Timesheet get details API", "normalHrs": null, "onCall": 1, "callOutList": [ { "startDate": "2023-11-20", "endDate": "2023-11-20", "startTime": "11:00", "endTime": "12:00", "description":"Callout description", "hrs": 0.5 } ], "ooh": null } |  | { "statusCode": 200, "status": "SUCCESS", "message": "Timesheet details saved successfully", "result": null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
3 | Employee | Edit Timesheet Entry | PATCH | /iapi/timesheet/details/{timesheetId} | 200 | 200 | Headers: userId:3276 { "timesheetId":1, "projectId": 1, "workOrderId": 1, "componentId": 1, "milestoneId": null, "projectXSubComponentId": 1, "startDate": "2023-11-20", "endDate": "2023-11-20", "startTime": "11:00", "endTime": "12:00", "entryType": 1, "description": "Worked on Timesheet get details API", "normalHrs": null, "onCall": 1, "callOutList": [ { "startDate": "2023-11-20", "endDate": "2023-11-20", "startTime": "11:00", "endTime": "12:00", "description":"Callout description", "hrs": 0.5 } ], "ooh": null } |  | { "statusCode": 200, "status": "SUCCESS", "message": "Timesheet details updated successfully", "result": null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
4 | Employee | Delete Timesheet Entry | DELETE | /iapi/timesheet/details/{timesheetId} | 200 | 200 | Headers: userId:3276 |  | { "statusCode": 200, "status": "SUCCESS", "message": "Timesheet entry deleted successfully", "result": null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
5 | Employee | Get Previous Timesheet Entry | GET | /iapi/timesheet/view/previousentry/{empId} | 200 | 200 | Headers: userId:3276 | Get particular type of timesheet entry:- entryType:normal,ooh,callout | { "statusCode": 200, "status": "SUCCESS", "message": "Previous timesheet details for employee retrived successfully", "result": [ { "timesheetId":1, "isSupportTimesheet":0, "isLeaveEntry":0, "date":"2023-01-01", "projectId":2, "projectName":"IAMT", "workOrderId":1, "workOrderNumber":"IAT1120232024", "componentId":1, "componentName":"Timesheet Development", "componentNumber":"IAT1120232024-1", "startTime":"11:00", "endTime":"12:00", "duration":"1 hr", "description":"TImesheet API work", "entryType":1, "activityId":1, "activityName":"Service Development", "phaseId":1, "phaseName":"Service Phase", "projecXSubCompId":null, "milestoneId":1, "milestoneName":"Timesheet API milestone", "callOutEntries":[ { "date":"2023-01-01", "startTime":"11:00", "endTime":"12:00", "duration":"1 hr", "description":"TImesheet API work call out" } ] } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
6 | Master | Get All Timesheet Status | GET | /iapi/timesheet/status | 200 | 200 | Headers: userId:3276 |  | { "statusCode": 200, "status": "SUCCESS", "message": "Timesheet status fetched Successfully", "result": [ { "statusId":1, "statusName":"Draft" }, { "statusId":2, "statusName":"Approved" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
7 | Reporting Manager Flow | View Timesheets | GET | /iapi/timesheet/view/rm | 200 | 200 | Headers: userId:3276 | projectId:1 workOrderId:1 compId:1 empId:3276 resourceType:"ACTIVE","INACTIVE","ALL" datafilter:"CURRWEEK","PREVWEEK", month:"FEB" startDate:"2023-01-01" endDate:"2023-01-30" viewType:"Detailed","Summary" view:"Daily","Monthly","Weekly" statusId:1 pageNo:1 pageOffset:10 | { "statusCode": 200, "status": "SUCCESS", "message": "Timesheet details fetched Successfully", "result": [ { "timesheetId":1, "timesheetDate":"2023-11-28", "projectId":1, "projectName":"IAMT 2023", "workorderId":1, "workorderName":"IAT0220232000", "componentId":1, "componentName":"IAT0220232000-1", "activityId":1, "activityName":"Development", "locationName":"Bangalore", "normalHrs":"2 hrs", "onCallHrs":"4 hrs", "callOutHrs":"2 hrs", "oohHrs":"1 hrs" }, { "timesheetId":1, "timesheetDate":"2023-11-29", "projectId":1, "projectName":"IAMT 2023", "workorderId":1, "workorderName":"IAT0220232000", "componentId":1, "componentName":"IAT0220232000-1", "activityId":1, "activityName":"Development", "locationName":"Bangalore", "normalHrs":"2 hrs", "onCallHrs":"4 hrs", "callOutHrs":"2 hrs", "oohHrs":"1 hrs" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null } Note: Response varies based on view type. Please check with figma screens for what need to be given as response
8 | Reporting Manager Flow | Download Timesheets | GET | /iapi/timesheet/view/rm/download | 200 | 200 | Headers: userId:3276 | projectId:1 workOrderId:1 compId:1 empId:3276 resourceType:"ACTIVE","INACTIVE","ALL" datafilter:"CURRWEEK","PREVWEEK", month:"FEB" startDate:"2023-01-01" endDate:"2023-01-30" viewType:"Detailed","Summary" view:"Daily","Monthly","Weekly" pageNo:1 pageOffset:10 | { "statusCode": 200, "status": "SUCCESS", "message": "Timesheet details downloaded Successfully", "result":null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
9 | Reporting Manager Flow | Get Reports | GET | /iapi/timesheet/reports | 200 | 200 | Headers: userId:3276 |  | { "statusCode": 200, "status": "SUCCESS", "message": "Report details fetched Successfully", "result":[ { "reportId":1, "reportName":"Timesheet under projectX" }, { "reportId":2, "reportName":"Effort Report" } ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
10 | Reporting Manager Flow | Get Report Details | GET | /iapi/timesheet/report/details | 200 | 200 | Headers: userId:3276 | reportId=1 departmentId=1 activityId=1 phaseId=1 projectId=1 pageNo:1 pageOffset:10 | { "statusCode": 200, "status": "SUCCESS", "message": "Report data fetched Successfully", "result":[ ], "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null } Note:Response array might vary for different reports. Please refer to figma for fields to display in output
11 | Reporting Manager Flow | Download Report Details | GET | /iapi/timesheet/report/details/download | 200 | 200 | Headers: userId:3276 | reportId=1 departmentId=1 activityId=1 phaseId=1 projectId=1 pageNo:1 pageOffset:10 | { "statusCode": 200, "status": "SUCCESS", "message": "Report data downloaded Successfully", "result":null, "error": null, "corelationId": "aacff7ad-a12d-4253-bf6f-621b3831bad8", "url": null }
12 | Reporting Manager Flow | Approve/Reject/Reopen Timesheet | PATCH | /iapi/timesheet/approvereject | 200 | 200 | Headers: userId:3276 [ { "empId": 3276, "timesheetDate": "2023-11-28", "startDate": "", "endDate": "", "month": "" }, { "empId": 3276, "timesheetDate": "", "startDate": "2023-01-01", "endDate": "2023-01-30", "month": "" }, { "empId":3276, "timesheetDate":"", "startDate":"", "endDate":"", "month":"FEB" } ] | statusId=1